## Slide 1
Status Meeting IV
Project 8: Entanglement in Online Choir
SNA-OSN-M Summer 2026 · Uni Bamberg × Uni Köln × HSLU
Presented by Hassan Ahmed
on behalf of the team
2026-06-11 · 14:00 CET

## Slide 2
What we said we'd do,Sprint 3 plan recap
Six deliverables. Four core, two pull-forward stretch. All six shipped.
Deliverable | Brief target | Status
WP1 audio on all Dagstuhl pieces | Jun 4 | ✓ done May 22
WP2 pose on 10 Tier-1 videos | Jun 11 | ✓ done May 22
WP3 Granger + COP-GC on 5 pieces | Jun 11 | ✓ done May 22
WP4 dashboard scaffold | Jun 11 | ✓ done May 22
E(t) end-to-end + null (stretch) | Jun 14 | ✓ done May 22 (23 days early)
WP3 full-corpus metrics (stretch) | Jun 14 | ✓ done May 22 (23 days early)

## Slide 3
Headline,E(t) works, 5/5 pieces beat null at p < 0.001
The Entanglement Index is operational end-to-end.
• All 5 Dagstuhl WP3 pieces tested.
• 200-shuffle circular-shift null per piece.
• Observed mean E(t): 0.57 to 0.80.
• Null mean: 0.48 to 0.61.
• Every piece > null by >17 σ.
• Pattern splits by piece, not size:
• LI 0.74-0.80, TP 0.57-0.68.

## Slide 4
WP1 audio scale,25 Dagstuhl musical takes
• Sprint 2: 1 piece (LI Quartet A Take 02).
• Sprint 3: all 25 musical takes across Locus Iste + Tu Pauper Es.
• 130 newly extracted singer parquets, 288 pairwise couplings.
• Total runtime: 78 minutes.
• Pipeline resumable; prefers DYN > HSM > LRX mic per singer.
• Pattern matches musical structure:
• Within-section (LI Basses): 0.78–0.87
• Full-choir polyphonic (TP): 0.40–0.53

## Slide 5
WP3 influence graph + COP-GC,Hacker flagship v2
• 5 pieces × 2 methods.
• Standard Granger + COP-GC (Zanin 2021).
• Sprint-2 reference reproduces:
• 11/12 edges, density 0.917, S leads.
• Method divergence,TP_FullChoir:
• Standard: 42/56 edges significant
• COP-GC: 25/56 edges significant
• Both methods carried forward.

## Slide 6
WP2 pose on 10 Tier-1 videos,5/10 pass detection floor
• Sprint 2: 1 video. Sprint 3: 10, stratified by NMP regime.
• Total runtime: 2.3 minutes.
• 5/10 pass 50% detection: ZKthfLPWBCQ 98.5%, Z-cH7j5iB3k 94.0%,
• ouFyQKszE_Y 79.5%, w0ywMP8mOc4 78.2%, VsnvueTan4I 66.7%.
• 5/10 fail: software-UI captures or dense low-res tile grids
• (no body for MediaPipe to find).
• Matches Status Meeting III "try and iterate" decision.
• 5 passing videos define WP2 inclusion set for H1.

## Slide 7
WP4 dashboard scaffold + E(t) integration
• Dashboard: React 18 + Vite 5 + TS strict + D3 + Plotly.
• Backend: FastAPI 0.111, 3 mock endpoints.
• 4 panels render end-to-end (Playwright-verified).
• Real-data wiring is the WP4 sub-plan (Jun 21).
•
• E(t) integration module:
• compute_entanglement() with NaN-safe weight reallocation.
• 200-shuffle circular-shift null at composite level.
• Tests: 23/23 pass.

## Slide 8
Sprint 4 plan,Jun 12 to Jun 25
Track | Sprint 4 work | Due
WP1 audio | Per-window Granger → time-varying N(t) | Jun 21
WP2 video | Pose on remaining 21 Tier-1 videos (triage) | Jun 30
WP3 network | Tier-3 latency injection: jitter on Dagstuhl audio | Jun 21
WP4 dashboard | Swap mock JSON → real parquet readers + pose overlay | Jun 21
Hard milestone: dashboard alpha runs on real data by Jun 21.

## Slide 9
Retrospective and four honest limitations
What worked
• 6/6 Sprint-3 deliverables shipped.
• 2 stretch items 23 days early.
• Doc-update discipline kept brief + guide + vault in sync after every phase.
What slipped
• ESMUC + ChoralSynth not acquired (proprietary / gate slipped May 15).
• To be revisited in Sprint 4 if licensing path opens.
Four honest limitations
• V(t) is NaN across all current E(t) (Dagstuhl is audio-only).
• WP3 corpus is all Dagstuhl studio,no NMP-regime variation yet.
• WP2 detection is 50%,the 5/10 pass rate defines our inclusion set.
• p_null reports as 0.0000,correct read is "p < 1/200", not literal zero.

## Slide 10
Open questions for the room
Three questions before we open the floor.
• To Prof. Hacker,do you have access to ESMUC or ChoralSynth multitrack data we could fold into Tier-2 before Sprint 4 acquisition?
• To Prof. Gloor,for the final paper figure, matplotlib-clean or Gephi/Cytoscape SVG-polished for the alchemical-stage diagram?
• To everyone,is the Jul 23 final presentation in-person at Bamberg or remote? Affects how Hassan and Hammad coordinate travel.
Thank you. Questions.