## Slide 1
STATUS MEETING II
Entanglement in Online Choir
Measuring coordination when singers cannot share the same room
Uni Bamberg
Uni Köln
HSLU
Presented by Zuraiz, on behalf of the team
Supervisors: Prof. Janine Hacker and Prof. Peter Gloor
audio + movement + influence
Notes: Good afternoon. Project 8, Entanglement in Online Choir. I am Zuraiz, presenting on behalf of the team. We are four members from Uni Bamberg. Our supervisors are Prof. Hacker on the Bamberg side and Prof. Gloor as COIN seminar lead. Thank you for the meeting slot.

## Slide 2
TEAM
Team complete; self-analysis is planned
02
Z
Zuraiz
Tree Hugger
73% Ant
Ant / Capybara
HA
Hammad Anwar
Tree Hugger
64% Ant
Capybara 49%
HS
Hassan Ahmed
Tree Hugger
63% Ant
Ant 40%
K
Kumaran Vasu
Tree Hugger
75% Ant
Ant 80%
Archetype results are included because the May 21 Virtual Mirror asks us to analyse our own team communication. The scientific contribution today is the choir dataset and measurement strategy.
Notes: Our team has four members, all M.Sc. students at Uni Bamberg. Three of us came from the chapter team; Kumaran joined at project signup. The archetype bars are here because the May 21 Virtual Mirror asks us to analyse our own team communication. For today, the important point is that the team is complete, role allocation is stable, and the self-analysis deliverable is planned.

## Slide 3
GOALS AND SCOPE
Can we quantify online choir coordination?
03
Research question
When a choir sings together over the internet, can we put a number on how well coordinated they are?
Where this comes from
NMP studies latency/tool quality. Coordination research studies group flow. Choirs give an objective acoustic outcome.
E(t) adapts Gloor's entanglement idea and Pentland's Honest Signals to choir audio/video; H1-H3 validate the adaptation.
E(t)
A(t) audio
V(t) visual
N(t) network
A proposed coordination index, not a pre-validated music metric.
H1
Low-latency tools score higher on E(t) than Zoom-class tools.
H2
Influence network shifts from democratic to leader-dominated.
H3
Body movement adds measurable explanatory power beyond audio.
Notes: Our research question is simple. When a choir sings together over the internet, can we put a number on how well coordinated they are? This question comes from a gap between two literatures. We are building a proposed number for that: E(t), the Entanglement Index. The formula is not copied directly from an online-choir paper; it is a domain adaptation inspired by Gloor's entanglement work and Pentland's Honest Signals. H1, H2, and H3 are the validation tests.

## Slide 4
DATASET STRATEGY
Four levels, four different jobs
04
Tier 1: real-world but messy
Tier 2: clean but academic
Tier 3: controlled and experimental
Tier 0
Seed URLs
5 Jamulus / Choir@Home URLs from Prof. Hacker
Guide search terms and inclusion rules
Starts the corpus search
Tier 1
YouTube virtual choirs
20-30 public videos, curated by May 15
Pose, mouth movement, visible synchrony, ensemble audio
Visual coordination / H3 sanity check
Tier 2
Academic multitrack
Dagstuhl ChoirSet, ESMUC, ChoralSynth
Separate singer tracks for pitch, onsets, Granger influence
A(t), N(t), directed graph
Tier 3
Latency injection
Artificial Zoom-class / low-latency versions of Tier 2
Add delay, jitter, packet loss, recompute E(t)
Clean H1 test
Key limitation
Tier 1 YouTube audio is mixed stereo, so H1 and the influence graph rely on Tier 2 and Tier 3.
Notes: The dataset strategy has three tiers plus one seed set. Tier 0 is five URLs from Prof. Hacker. Tier 1 is real-world but messy: public YouTube virtual choir videos for visual coordination. Tier 2 is clean but academic: multitrack recordings where each singer has a separate track. Tier 3 is controlled and experimental: we create it from Tier 2 by adding latency, jitter, and packet loss. In one sentence: Tier 0 gives seed examples, Tier 1 gives real-world video, Tier 2 gives clean per-singer audio, and Tier 3 gives controlled latency experiments.

## Slide 5
OVERALL PROJECT PLAN
Plan: scope now, build next, synthesize in July
05
Phase 1
Apr 16-Apr 30
Scope, dataset strategy, repo scaffold
Phase 2
May 1-Jul 7
Audio, video, network pipelines; E(t)
Phase 3
Jul 8-Jul 31
Paper, dashboard, final presentation
VS#1 Apr 16
VS#2 Apr 30
VS#3 May 21
VS#4 Jun 11
VS#5 Jun 25
VS#6 Jul 9
Final Jul 23
Done today
Research question and hypotheses defined
Data tiers clarified
Repo scaffold ready
Seed URLs recorded
Next
Tier 2 datasets on disk
Tier 1 corpus curated
Video pose data
Influence graph pipeline
Later
E(t) end-to-end
Dashboard alpha
Paper draft v1
Final presentation and paper
Notes: We split the 14 weeks into three phases. Phase 1 closes today with the research question, hypotheses, data tiers, and repo scaffold in place. The honest status is: we have seed URLs, but we have not yet collected the analysis corpus or extracted features. That starts in Phase 2. Zero feature code yet. The audio pipeline lands May 8. We are on schedule and there are no critical blockers.

## Slide 6
NEXT ITERATION
Sprint 2 turns the data strategy into files
06
Audio pipeline
May 8
Pull Tier 2 datasets; run pitch tracking and onset detection.
Per-singer feature parquet for 5 pieces
Video pipeline
May 22
Run MediaPipe Pose and FaceMesh on first 10 YouTube videos.
Pose parquet + calibration note
Curated corpus
May 15 / 21
Hand-curate 20-30 videos; file DPIA outline.
Corpus manifest + DPIA outline
Virtual Mirror
May 21
Export team WhatsApp; run SocialCompass tools.
Mirror write-up for VS#3
Dataset order
Tier 2 on disk first -> Tier 1 curated second -> Tier 3 generated from Tier 2 after audio pipeline runs.
Notes: Sprint 2 runs from April 30 to May 21. First, the audio pipeline pulls the academic multitrack datasets to disk and outputs per-singer feature parquet by May 8. Second, the video pipeline starts pose and face tracking. Third, the curated YouTube corpus and GDPR work produce the corpus manifest and DPIA outline. Fourth, the Virtual Mirror produces the team self-analysis for May 21. If asked what exactly happens next: Tier 2 on disk first, Tier 1 curated second, then Tier 3 generated from Tier 2.

## Slide 7
WAY OF WORKING
A lightweight operating rhythm for a short research build
07
Cadence
3-week sprints
Pre-VS review 1-2 days before
Each sprint ends in an artefact
Status meetings as checkpoints
Sync
Weekly 30-minute team sync
Daily async status posts
WhatsApp + GitHub Issues
Weekly check-in with Prof. Hacker
Toolstack
Python analysis pipeline
Git + GitHub Actions
Markdown source of truth
Peer review through PRs
Virtual Mirror link: our WhatsApp group is both the coordination channel and the May 21 self-analysis input.
Notes: Three pillars: cadence, sync, and toolstack. Cadence: three-week sprints aligned to status meetings, each ending in a defined artefact. Sync: weekly team meeting, daily async status posts, WhatsApp and GitHub Issues, plus a weekly check-in with Prof. Hacker. Toolstack: Python, Git and GitHub Actions, Markdown as source of truth, and peer review through pull requests. The team WhatsApp group is also our input data for the Virtual Mirror on May 21.

## Slide 8
THANK YOU
Questions welcome
Project 8: Entanglement in Online Choir
Zuraiz, on behalf of the team
Notes: That covers our team, scope, dataset strategy, project plan, next iteration, and way of working. Thank you for listening. I am happy to take your questions.